## Slide 1
Practical advice on Twining working methods and management issues
DG Enlargement – Unit D2
November 2013
Presentation to
Ukrainian Institutions
Twinning after Manual 2017
Claus Lech
Team Leader Twinning
DG NEAR – Unit C 3
Notes: Present yourself and your background.
Good morning, my name is

## Slide 2
Nothing is possible without individuals.
Nothing is lasting without institutions
Jean Monnet
("men" changed to "individuals")

## Slide 3: What is particular about “Twinning”
Twinning is a tool for institution building
- Where a joint effort by homologues from a Partner Country administration and one/more EU Member State administrations
- creates a partnership between staff in a Partner Country administration and their homologues in one/more EU MS
Notes: A Twinning is a project between Public Administrations – from European Union (EU) Member State(s) (MS) and the similar Public Administration form a Partner Country in the Pre-accession (IPA) Region or neighbourhood Region. (ENI)

## Slide 4: What is particular about “Twinning”
- where the partners in the programming has defined objectives and mandatory results to be achieved based on requirements agreed in the policy dialogue
- making the partners jointly responsible for the results but only the Partner Country for sustaining these
The selection is not based on price, but on methodology, structure, the quality of the RTA and the accessibility to expertise defined by the EU MS (not ST CVs)

## Slide 5: What is particular about “Twinning”
All EU MS are consulted at same time via the Network of National Contact Points (usually in MoFA) in all EU MS
A majority of costs are pre-defined in a Commission Decision as compensation to the EU MS engaging.
Work-plans are jointly developed after the Partner Country has selected its partner.
A Twinning Review Mission will check status 6-12 months after project has ended. Are results sustained?

## Slide 6: Twinning – Lessons learnt
Twinning Reform focussed on
Simplification of all processes
Speed (contracting and start) & Flexibility (implementation)
Common rules for Twinning for IPA/ENI
A solid and simple Compensation model for all EU MS
Protecting the key concepts behind Twinning
One year down the line – lessons learned – practical recommendations

## Slide 7: Twinning - Always remember ….
0. Institutional setting and political implications
The EU MS are always represented by a high level appointed Project Leader empowered to commit the EU MS or body engaging
The RTAs are usually supervised by this EU MS PL and in frequent if not daily contact with the PL.
The whole Twinning cycle is closely monitored by National Contact Point(s) established (usually in the MoFAs) in each EU MS and PC
EU HQ relevant services are always involved in project definition.

## Slide 8: Twinning – Project Cycle
1. Programming – key elements
Ensure political support from the top, reiterate link to agreements in the policy dialogue and justify how this contributes to ongoing reforms
Define why Twinning is the best tool in the toolbox for the sector/subsector you want to change and ensure that you on the PC side have the capacity to handle (HR, funds etc) and absorb
Ensure complementarity with other on-going actions (donors/ PC own initiatives) and analyse sequencing and non-dependency on results of other (TA/SUP/WORKS/Grant) projects/investments.

## Slide 9: Twinning – Project Cycle
2. Project Preparation - key elements
Put realistic results and focus on the most important. Use the best expertise to assist you to define.
Define objectives and results not activities
Indicate key project milestones but don’t detail sequencing
Consider EUD and MS Embassy engagement in the communication/visibility planning
Carefully analyse the need for study tours.
Notes: Use best expertise to assist on the Twinning Fiche description.

## Slide 10: Twinning – Project Cycle
3. Publication, proposals and Selection of Partner
Publish the call and send it to call EU MS NCPs as soon as you have the OK by the Twinning Inter-Service Group in EU HQ. React as quickly as possible to the ”opinion” given by EU HQ.
Focus your selection of partner on the one best fitting needs/wishes – meaning focus on the offered methodology, structure used by EU MS, the quality of RTA and the accessibility to expertise defined by the EU MS – do not focus on costs – they are to be a large extent regulated in the Commission Decision.

## Slide 11: Twinning – Project Cycle
4. Contract
PC and MS and CA to agree a detailed contract preparation timetable - the selected partner has to provide all information for the contract asap.
Contract at the signature stage is ”sketchy” and only defined at budget heading level and the flat rate budgetlines (contingency/reserve 2,5% and flat indirect 6%) -> Process an addendum after the first Steering Committee
Since all contract cost details - for the first 6 months is only developed at the time when the initial rolling work-plan is agreed

## Slide 12: Twinning – Project Cycle
5. Implementation
- The rolling work plan is the key document for all partners defining what, when, who, where for six-months rolling periods. Invest sufficient resources in developing it.
- A Steering Committee meeting every 3 months is composed of high-level representatives from the Partner Country and the EU MS(s) – (PLs) – steers the project and approve all work-plans. Do dedicate more time to prepare for these. At each SC carefully monitor remaining funds.
- For all Steering Committees all relevant stakeholders in the sector/sub-sector in which the project works, should be invited as observers for the Committee. Do analyse and involve the EUD when discussing who should be part (as observers).

## Slide 13: Twinning – Project Cycle
- The Partner Country should check at Twinning Fiche stage and recheck well before the RTA arrival that adequate office space, meeting rooms etc are available.
- Partner country RTA Counterpart should be fully available and make sure that the RTA is assisted until RTA Assistants recruited
- All partners should engage fully in work-plan preparations as soon as the RTA has arrived – remember to ensure all related departments are on board
- Set aside sufficient time for discussing communication/visibility
- Involve all relevant departments/agencies/institutions in the work-programme planning – public reforms are rarely limited to only one entity (ex - customs -> revenue - taxes - police etc)

## Slide 14: Twinning – Project Cycle
6. End of project and evaluation of results
- Final reports always deliver a set of recommendations for the Partner Country to take after end of project
- The Partner Country administration should carefully plan (also ask resources to implement) such follow up activities
- A Twinning Review Mission is then undertaken 6-12 months after project end
- Twinning project are in addition evaluated as part of larger (sector/global) HQ-evaluations.
- Elgibility of costs under Individual Twinning contracts are randomly checked by auditors.

## Slide 15: Standard Twinning
Project involves a resident twinning
adviser (RTA) from 12 up to 36 months,
and a number of short-term experts
coming from the EU MS administration(s) implementing the twinning...
The mobilisation of both administrations is ensured through the designation of their respective project leaders (high level civil servants) the MS PL and Partner Country PL.
Budgets (averages) between 1,5 and 1,8 M€
Reminder

## Slide 16: Twinning Light
No RTA
8 months (exceptionally up to max 10)
A PL and a number of short-term experts from the EU MS administration(s) implementing the Twinning...
The mobilisation of both administrations is ensured through the designation of their respective project leaders (high level civil servants) - the MS PL and Partner Country PL.
Max budget: 250.000€
Reminder

## Slide 17: Manual Update June 2018
Currently processing a revised manual – not changing any core principles/concepts, but
Clarifying
Adding more examples
Giving further details
Ensuring full text coherence
Adding a contractual element – required by CoA
Updating references (new Regulations etc)

## Slide 18: Further material for studying

## Slide 19: Twinning means engagement by …
Public administrations (and Mandated Bodies)
MS NCP
Beneficiary Administration(s)
CFCU (IPA)-PAO-offices (ENI)
EU Delegation (Twinning focal point/Press and information Officer/PAR coordinator)
EC Headquarters (DG NEAR, C3)
Project Leaders, Resident Twinning Advisers, Component Leaders,
Short Term Experts
Other donors/partners
Twinning stakeholders

## Slide 20: PC Administration, CA, EUD and EU HQ have crucial roles
The Partner Country administration is the one reacting to requirements/needs arising from the policy dialogue with EU and/or reform developments in the the Partner Country
Contracts are signed by the Contracting Authority and the EU MS PL, - and Work-plans are also signed by EU MS and PC Project leaders.
Role of Contracting Authority (CA)- always to be the one to circulate the fiches to MSs (standard and twinning light) and always the entity preparing the contract
Publication always by EUD even if indirect management mode;
HQs entities gives an Opinion on the fiche
Selection procedure is by consensus – also acceptance by EUD;
Who does what?

## Slide 21: Type of Activities
The rolling work-plan will likely consist of actions línked to:
- Legal harmonisation or approximation
- Contribution to policy/strategy documents
- Standards/norms/accreditation/certification/best practice
- Institutional capacity building
- Mission of Short term experts
- Study visits, Trainings and Internships
- Communication/Visibility actions
- Workshops (NB: Complementarity (incl TAIEX)
What actions?

## Slide 22: The Selection Meeting
Both the written proposal and the oral presentation will be assessed.
The PC delegation should include at least the Project Leader and RTA counterpart and the BC NCP (PAO, CFCU); The MS delegation should always include the proposed Project Leader and RTA(s).
During the selection meeting, for each proposal approximately 45 minutes are given to the presentation of the MS and 30 minutes for Q/A.
How to select?

## Slide 23: Rolling Workplan and corresponding budget
Prepared by the RTA and RTA Counterpart upon arrival of RTA, the first six months duration rolling Work plan consisting of a sequence of activities and CVs of short term experts, is approved during first steering committee and reviewed/updated quarterly. Invest sufficient time, energy and political commitment.
The Twinning work plan details the relevant organisation and methods, including work and time schedule, a very precise division of tasks between the partners and a detailed breakdown of costs. At each Steering Committee meeting carefully monitor remaining funds vs mandatory results
Planning the implementation?

## Slide 24: Costs covered and Communication/Visibility
A Commission Decision - regulates the costs under Twinning and defines how to ensure that Twinning operates on No-profit principles as per EU Financial Regulation. EU MS are compensated.
Communication/visibility - Twinning projects are not bilateral but EU projects – but can of course later be followed by bilateral projects. Reach out to the Public – agree a Communication /Visibility Plan with the EUD. Involve appropriate political levels.
NB: Always consider how Twinning and TAIEX can complement each others - no duplication allowed
Costs and Visibility

## Slide 25: Role of EU HQ
Twinning Coordination Team monitors all Twinning implementation, advises, statistics, conflicts (if EUD cannot)
- Reviews the Twinning fiche already approved by the PAR manager appointed by the Contracting Authority and subsequenlty sent to the Twinning coordination team
- Ask further reviews to the line DGs, CoTEs (including PAR), TAIEX country coordinators in C3, GEO desks and EEAS (the same entities being involved also in sector policy dialogues)
- Ensures that an opinion on the fiche is issued to the Contracting Authority in time. The Opinion can be:
EU HQ –TISG process

## Slide 26: Opinion on Twinning Fiche
1 Full approval: the Twinning Fiche is approved as submitted and can be circulated;
2 Approval with Comments: the Twinning Fiche is approved, but improvements and/or adaptations could be introduced before circulation;
3 Conditional approval: the Twinning Fiche is approved, but specific amendments must be introduced by the Contracting Authority before circulation;
4 Rejection: the Twinning Fiche is rejected and all parties involved in its preparation are invited to re-submit a modified draft to the Twinning Inter-service group.
EU HQ opinion

## Slide 27: Evaluation of results
EU Delegation/CA triggers
Based on Final Report of project
2 experts (RTA + former RTA or other expert)
App. 5 days
Obligation to provide a report.
Organized and financed by TAIEX
Twinning Review Missions

## Slide 28: Twinning history
Launched in May 1998 to support the Partner Countries having applied for accession to the EU family of Member States (accessions 2004, 2007) (Phare->IPA)
Accession criteria:
- Copenhagen Criteria setting the criteria for Membership of the EU related to the applicants was established in 1993 and includes that for a country to accede it must accept the Union Acquis
Tight resources and timetable -> focus on hard acquis ->
-> focus on legal harmonisation
Accession Countries

## Slide 29: Twinning history
What is the Union Acquis?
The acquis is the body of common rights and obligations that is binding on all the EU member states. It is constantly evolving and comprises:
  the content, principles and political objectives of the Treaties;
  legislation adopted pursuant to the Treaties and the case law of the Court of Justice;
  declarations and resolutions adopted by the Union;
  instruments under the Common Foreign and Security Policy;
  international agreements concluded by the Union and those entered into by the member states among themselves within the sphere of the Union's activities
Notes: NB: Hard Acquis and Soft Acquis

## Slide 30: Twinning history
Twinning expanded to also work with Neighbourhood countries In 2004 – and in future could be expanded further.
Twinning in ENI countries responds to cooperation or other agreements of very different nature. 20 priorities by 2020. Belarus first project in 2017.
Focus – often more on Economic Development and standard/norms for trade etc (customs standard etc)
  ENI
Notes: In 2004 The Twinning instrument was also made available to Neighbourhood countries
It aims at upgrading/modernising an administration though training, reorganisation as well as drafting of laws and regulations through legal approximation
...and to respond to agreements (cooperation or association).

## Slide 31: WHERE?
EU MS 28 countries
Instrument for Pre-Accession Assistance (IPA)
(in light blue)
7 partners
Albania
Bosnia and Herzegovina
Kosovo*
Montenegro
Serbia
Turkey
the former Yugoslav Republic of Macedonia
∗ This designation is without prejudice to positions on status, and is in line with UNSCR 1244 and the ICJ Opinion on the Kosovo Declaration of Independence
IPA
Notes: Croatia special case conferred management power without ex ante control, very active in circulating Twinning fiches mostly TWG lights until December 2016 and participating in calls most of the time as junior partner
Iceland

## Slide 32: WHERE ? ENI
 | ENI Countries (in orange) Morocco Algeria Tunisia Libya* Egypt Israel Palestine Jordan Lebanon Syria* Armenia Georgia Azerbaijan Ukraine Moldova Belarus
ENI

## Slide 33: Twinning in numbers since 1998 IPA+ENI
More than €2 Billion
Budget expenditure
More than 2,700
Twinning projects circulated
Justice, Agriculture,
and Finance
Main sectors

## Slide 34: More information available on:
Twinning website: http://ec.europa.eu/twinning

## Slide 35
Questions?